## Executive Summary
Dimension | Current Baseline | Final Target | Gap | Timeline
Data Volume | ~14K records, ~55 variables, single PostgreSQL (~50MB) | 10TB across distributed storage | ~99.999% gap | 12 months
Model Accuracy (Direction) | Unmeasured (~50% theoretical baseline) | 90% | ~40% improvement | 12 months
Exploitation Metrics Accuracy | Just implemented viability scoring, unvalidated | 90% | ~40% improvement | 12 months
Deployment Time (E2E) | 30-45 min build + manual GitHub/Stripe/analytics = several hours | 2 hours fully automated | Automation gap | 12 months
Build Error Rate | Unmeasured, no systematic tracking | <5% | Tracking + improvement needed | 12 months
Pricing Intelligence | Fixed tiers ($0-$199.99), no geo-pricing | Region/economy-specific dynamic pricing | Not started | 12 months
Revenue Dashboard | Stripe in systems3 only, no cross-app | Central dashboard, all apps, all revenue streams | Not started | 12 months
Self-Improvement | Legacy retrain code (non-operational) | Continuous learning, auto-tuning, feedback loops | Not started | 12 months
Deployed Apps | 1 (Causal Affect) + 1 (systems3-project-reporter) | 4-10 apps (per AMP) | 2-8 more apps | 12 months
Key Decisions
Timeline: 12 months (~8 milestones at ~6 weeks each)
App scope: 4-10 apps (per AMP plan)
Data sources: All — social/financial feeds, news/search trends, IoT/sensor
Storage evolution: PostgreSQL → TimescaleDB → S3 cold storage + hot cache

## MS Project
WBS | Task Name | Duration (days) | Start | Finish | Outline Level
1 | M0 - Instrument & Measure | 15 | 2026-03-09 | 2026-03-27 | 1
1.1 | Track A: Model Accuracy Baseline | 15 | 2026-03-09 | 2026-03-27 | 2
1.1.1 | Run prediction validation on all matured predictions: POST /predictions/validate | 3 | 2026-03-09 | 2026-03-12 | 3
1.1.2 | Record baseline direction_accuracy, avg_error_pct, avg_change_error_pct | 3 | 2026-03-13 | 2026-03-16 | 3
1.1.3 | Add automated weekly validation cron (APScheduler or Railway cron) | 3 | 2026-03-17 | 2026-03-20 | 3
1.1.4 | Add accuracy trend chart to Prediction Accuracy tab | 5 | 2026-03-21 | 2026-03-27 | 3
1.2 | Track B: Build Error Baseline | 15 | 2026-03-09 | 2026-03-27 | 2
1.2.1 | Add BuildMetrics tracking to build_feature.py (syntax/test/frontend/wiring errors) | 5 | 2026-03-09 | 2026-03-15 | 3
1.2.2 | Store results in JSON artifact uploaded with GitHub Actions | 5 | 2026-03-16 | 2026-03-22 | 3
1.2.3 | Parse artifact in a /builds/metrics endpoint | 5 | 2026-03-23 | 2026-03-27 | 3
1.3 | Track C: Exploitation Metrics Baseline | 15 | 2026-03-09 | 2026-03-27 | 2
1.3.1 | Tag all 103 BUILD recommendations with viability scores | 5 | 2026-03-09 | 2026-03-15 | 3
1.3.2 | Manually validate 10-20 BUILD recommendations against real-world outcomes | 5 | 2026-03-16 | 2026-03-22 | 3
1.3.3 | Create exploitation_validation table for outcome tracking | 5 | 2026-03-23 | 2026-03-27 | 3
1.4 | Track D: Revenue Baseline | 15 | 2026-03-09 | 2026-03-27 | 2
1.4.1 | Audit Stripe dashboard for current subscriber count and MRR | 7 | 2026-03-09 | 2026-03-17 | 3
1.4.2 | Document current revenue per app | 8 | 2026-03-18 | 2026-03-27 | 3
1.5 | M0 - Instrument & Measure Complete | 0 | 2026-03-27 | 2026-03-27 | 1
2 | M1 - Foundation Scaling | 30 | 2026-03-30 | 2026-05-08 | 1
2.1 | Track A: Model Accuracy → 60% | 30 | 2026-03-30 | 2026-05-08 | 2
2.1.1 | Add daily Wikipedia pageview ingestion (55 vars × 365 days = 20K new records/year) | 7 | 2026-03-30 | 2026-04-07 | 3
2.1.2 | Add daily Reddit activity ingestion for top 30 subreddits | 7 | 2026-04-08 | 2026-04-16 | 3
2.1.3 | Implement walk-forward validation (train on N months, predict N+1, slide) | 7 | 2026-04-17 | 2026-04-25 | 3
2.1.4 | Add multi-lag Granger testing (1-12 month lags) | 10 | 2026-04-26 | 2026-05-08 | 3
2.2 | Track B: Build Errors → 25% | 30 | 2026-03-30 | 2026-05-08 | 2
2.2.1 | Add pre-build template validation (lint templates before generation) | 10 | 2026-03-30 | 2026-04-12 | 3
2.2.2 | Add automated import resolution (detect missing imports, auto-add) | 10 | 2026-04-13 | 2026-04-26 | 3
2.2.3 | Add structured error reporting to GitHub Actions artifacts | 10 | 2026-04-27 | 2026-05-08 | 3
2.3 | Track C: Exploitation Accuracy → 55% | 30 | 2026-03-30 | 2026-05-08 | 2
2.3.1 | Backtest viability scores against 6-month historical data | 10 | 2026-03-30 | 2026-04-12 | 3
2.3.2 | Calibrate viability scoring weights based on backtest results | 10 | 2026-04-13 | 2026-04-26 | 3
2.3.3 | Add target_growth_actual field for outcome tracking | 10 | 2026-04-27 | 2026-05-08 | 3
2.4 | Track D: Data Infrastructure | 30 | 2026-03-30 | 2026-05-08 | 2
2.4.1 | Enable TimescaleDB extension on Railway PostgreSQL | 6 | 2026-03-30 | 2026-04-06 | 3
2.4.2 | Convert time_series_data to hypertable with time-based partitioning | 6 | 2026-04-07 | 2026-04-14 | 3
2.4.3 | Add automated data retention policy (raw: 2 years, aggregated: forever) | 6 | 2026-04-15 | 2026-04-22 | 3
2.4.4 | Set up S3 bucket for cold storage archive | 6 | 2026-04-23 | 2026-04-30 | 3
2.4.5 | Connection pool tuning: pool_size=20, max_overflow=10 | 6 | 2026-05-01 | 2026-05-08 | 3
2.5 | Track E: Revenue Dashboard v1 | 30 | 2026-03-30 | 2026-05-08 | 2
2.5.1 | Create RevenueEvent model (app_id, event_type, amount, currency, region, timestamp) | 7 | 2026-03-30 | 2026-04-07 | 3
2.5.2 | Create /revenue/dashboard endpoint aggregating across all Stripe accounts | 7 | 2026-04-08 | 2026-04-16 | 3
2.5.3 | Wire Stripe webhook events for all deployed apps to central tracker | 7 | 2026-04-17 | 2026-04-25 | 3
2.5.4 | Build basic Revenue tab (MRR chart, subscriber count, per-app breakdown) | 10 | 2026-04-26 | 2026-05-08 | 3
2.6 | M1 - Foundation Scaling Complete | 0 | 2026-05-08 | 2026-05-08 | 1
3 | M2 - Intelligence Layer | 30 | 2026-05-11 | 2026-06-19 | 1
3.1 | Track A: Model Accuracy → 65% | 30 | 2026-05-11 | 2026-06-19 | 2
3.1.1 | Add ensemble model: Granger causality + linear regression + ARIMA | 7 | 2026-05-11 | 2026-05-19 | 3
3.1.2 | Implement confidence-weighted ensemble (weight by historical accuracy) | 7 | 2026-05-20 | 2026-05-28 | 3
3.1.3 | Add feature engineering: rolling averages (7d/30d/90d), rate of change, volatility | 7 | 2026-05-29 | 2026-06-06 | 3
3.1.4 | Add cross-validation signal confidence (Wikipedia + Reddit agreement score) | 10 | 2026-06-07 | 2026-06-19 | 3
3.2 | Track B: Build Errors → 20% | 30 | 2026-05-11 | 2026-06-19 | 2
3.2.1 | Add AI-powered code review step (LLM validates before commit) | 10 | 2026-05-11 | 2026-05-24 | 3
3.2.2 | Add integration test templates for common patterns (CRUD, auth, Stripe) | 10 | 2026-05-25 | 2026-06-07 | 3
3.2.3 | Fix top 5 most common build failure patterns from M1 data | 10 | 2026-06-08 | 2026-06-19 | 3
3.3 | Track C: Exploitation Accuracy → 60% | 30 | 2026-05-11 | 2026-06-19 | 2
3.3.1 | Add Google Trends integration (pytrends with proxy rotation) | 10 | 2026-05-11 | 2026-05-24 | 3
3.3.2 | Cross-reference viability scores with Google Trends search volume | 10 | 2026-05-25 | 2026-06-07 | 3
3.3.3 | Add competition scoring from real arXiv citation counts | 10 | 2026-06-08 | 2026-06-19 | 3
3.4 | Track D: Build Automation → 4 hours | 30 | 2026-05-11 | 2026-06-19 | 2
3.4.1 | Automate GitHub repo creation via GitHub API | 7 | 2026-05-11 | 2026-05-19 | 3
3.4.2 | Auto-generate Railway project via Railway API | 7 | 2026-05-20 | 2026-05-28 | 3
3.4.3 | Auto-wire Stripe subscription (create product + price via API) | 7 | 2026-05-29 | 2026-06-06 | 3
3.4.4 | Auto-inject GA4 measurement ID from analytics template | 10 | 2026-06-07 | 2026-06-19 | 3
3.5 | Track E: Data Scale → 500GB | 30 | 2026-05-11 | 2026-06-19 | 2
3.5.1 | Add FRED economic indicators (50+ variables: GDP, CPI, unemployment) | 7 | 2026-05-11 | 2026-05-19 | 3
3.5.2 | Add Alpha Vantage intraday data for top 10 stocks (5-min intervals) | 7 | 2026-05-20 | 2026-05-28 | 3
3.5.3 | Add news sentiment from GDELT API (daily event counts by theme) | 7 | 2026-05-29 | 2026-06-06 | 3
3.5.4 | Set up ETL pipeline with batch scheduling (APScheduler) | 10 | 2026-06-07 | 2026-06-19 | 3
3.6 | M2 - Intelligence Layer Complete | 0 | 2026-06-19 | 2026-06-19 | 1
4 | M3 - Self-Learning Foundation | 30 | 2026-06-22 | 2026-07-31 | 1
4.1 | Track A: Model Accuracy → 70% | 30 | 2026-06-22 | 2026-07-31 | 2
4.1.1 | Implement automatic model retraining when accuracy drops below threshold | 7 | 2026-06-22 | 2026-06-30 | 3
4.1.2 | Add prediction feedback loop: validated predictions → retrain features | 7 | 2026-07-01 | 2026-07-09 | 3
4.1.3 | Add anomaly detection (Z-score) to flag unusual signals | 7 | 2026-07-10 | 2026-07-18 | 3
4.1.4 | Implement adaptive lag selection (dynamically adjust based on recent accuracy) | 10 | 2026-07-19 | 2026-07-31 | 3
4.2 | Track B: Build Errors → 15% | 30 | 2026-06-22 | 2026-07-31 | 2
4.2.1 | Build error pattern classifier (import, syntax, config, runtime categories) | 10 | 2026-06-22 | 2026-07-05 | 3
4.2.2 | Auto-fix common patterns (missing __init__.py, wrong imports, missing env vars) | 10 | 2026-07-06 | 2026-07-19 | 3
4.2.3 | Add scaffold regression tests (test each template produces working code) | 10 | 2026-07-20 | 2026-07-31 | 3
4.3 | Track C: Exploitation Accuracy → 65% | 30 | 2026-06-22 | 2026-07-31 | 2
4.3.1 | Track actual outcomes of PURSUING recommendations | 10 | 2026-06-22 | 2026-07-05 | 3
4.3.2 | Add time-to-market analysis (recommendation → live product duration) | 10 | 2026-07-06 | 2026-07-19 | 3
4.3.3 | Calibrate opportunity_duration_months against actual windows | 10 | 2026-07-20 | 2026-07-31 | 3
4.4 | Track D: Build Automation → 3 hours | 30 | 2026-06-22 | 2026-07-31 | 2
4.4.1 | Add automated domain configuration (subdomain allocation) | 7 | 2026-06-22 | 2026-06-30 | 3
4.4.2 | Add automated SSL certificate provisioning | 7 | 2026-07-01 | 2026-07-09 | 3
4.4.3 | Add automated database setup for deployed apps | 7 | 2026-07-10 | 2026-07-18 | 3
4.4.4 | Add post-deploy health check + smoke test | 10 | 2026-07-19 | 2026-07-31 | 3
4.5 | Track E: Data Scale → 1TB | 30 | 2026-06-22 | 2026-07-31 | 2
4.5.1 | Add social media feeds (Twitter/X academic API for trend data) | 7 | 2026-06-22 | 2026-06-30 | 3
4.5.2 | Add IoT starter: OpenWeather API for 100 cities (hourly) | 7 | 2026-07-01 | 2026-07-09 | 3
4.5.3 | Add Pushshift/Pullpush for full Reddit historical data | 7 | 2026-07-10 | 2026-07-18 | 3
4.5.4 | Implement data compression in TimescaleDB (compress chunks >7 days old) | 10 | 2026-07-19 | 2026-07-31 | 3
4.6 | Track F: Pricing Intelligence v1 | 30 | 2026-06-22 | 2026-07-31 | 2
4.6.1 | Add IP geolocation to dashboard (MaxMind GeoLite2 free database) | 7 | 2026-06-22 | 2026-06-30 | 3
4.6.2 | Map regions to PPP tiers from World Bank API | 7 | 2026-07-01 | 2026-07-09 | 3
4.6.3 | Create pricing_recommendation table (region, suggested_price, confidence) | 7 | 2026-07-10 | 2026-07-18 | 3
4.6.4 | Add traffic-based demand estimation per region | 10 | 2026-07-19 | 2026-07-31 | 3
4.7 | M3 - Self-Learning Foundation Complete | 0 | 2026-07-31 | 2026-07-31 | 1
5 | M4 - Scale & Optimize | 30 | 2026-08-03 | 2026-09-11 | 1
5.1 | Track A: Model Accuracy → 75% | 30 | 2026-08-03 | 2026-09-11 | 2
5.1.1 | Add LSTM/transformer-based time series model (PyTorch) as ensemble member | 7 | 2026-08-03 | 2026-08-11 | 3
5.1.2 | Implement feature importance ranking (SHAP values) for interpretability | 7 | 2026-08-12 | 2026-08-20 | 3
5.1.3 | Add regime detection (bull/bear/sideways affect model choice) | 7 | 2026-08-21 | 2026-08-29 | 3
5.1.4 | Implement online learning (update model incrementally with new data) | 10 | 2026-08-30 | 2026-09-11 | 3
5.2 | Track B: Build Errors → 10% | 30 | 2026-08-03 | 2026-09-11 | 2
5.2.1 | Implement AI-powered scaffold improvement (analyze fails → update templates) | 10 | 2026-08-03 | 2026-08-16 | 3
5.2.2 | Add end-to-end integration test suite for full build pipeline | 10 | 2026-08-17 | 2026-08-30 | 3
5.2.3 | Add canary deployment (deploy to staging first, promote if healthy) | 10 | 2026-08-31 | 2026-09-11 | 3
5.3 | Track C: Exploitation Accuracy → 70% | 30 | 2026-08-03 | 2026-09-11 | 2
5.3.1 | Add competitive landscape analysis (how many similar apps exist?) | 10 | 2026-08-03 | 2026-08-16 | 3
5.3.2 | Cross-reference with Product Hunt / Indie Hackers for market validation | 10 | 2026-08-17 | 2026-08-30 | 3
5.3.3 | Add user engagement prediction model (predict DAU/MAU) | 10 | 2026-08-31 | 2026-09-11 | 3
5.4 | Track D: Build Automation → 2.5 hours | 30 | 2026-08-03 | 2026-09-11 | 2
5.4.1 | Add automated testing pipeline for deployed apps | 10 | 2026-08-03 | 2026-08-16 | 3
5.4.2 | Add automated monitoring setup (uptime, error rate, performance) | 10 | 2026-08-17 | 2026-08-30 | 3
5.4.3 | Add automated changelog and release notes generation | 10 | 2026-08-31 | 2026-09-11 | 3
5.5 | Track E: Data Scale → 3TB | 30 | 2026-08-03 | 2026-09-11 | 2
5.5.1 | Add Bloomberg/Reuters alternative data feeds (if budget allows) | 10 | 2026-08-03 | 2026-08-16 | 3
5.5.2 | Add satellite imagery analysis for economic indicators (nighttime lights) | 10 | 2026-08-17 | 2026-08-30 | 3
5.5.3 | Implement data lakehouse pattern (S3 + DuckDB + PostgreSQL hot data) | 10 | 2026-08-31 | 2026-09-11 | 3
5.6 | Track F: Revenue Dashboard v2 | 30 | 2026-08-03 | 2026-09-11 | 2
5.6.1 | Add Google AdSense integration for ad-supported apps | 7 | 2026-08-03 | 2026-08-11 | 3
5.6.2 | Add per-app P&L tracking (revenue - infrastructure cost) | 7 | 2026-08-12 | 2026-08-20 | 3
5.6.3 | Add subscriber cohort analysis (retention by signup month) | 7 | 2026-08-21 | 2026-08-29 | 3
5.6.4 | Add revenue forecasting from growth trends | 10 | 2026-08-30 | 2026-09-11 | 3
5.7 | M4 - Scale & Optimize Complete | 0 | 2026-09-11 | 2026-09-11 | 1
6 | M5 - Autonomous Operations | 30 | 2026-09-14 | 2026-10-23 | 1
6.1 | Track A: Model Accuracy → 80% | 30 | 2026-09-14 | 2026-10-23 | 2
6.1.1 | Implement multi-horizon forecasting (1 week, 1 month, 3 month predictions) | 7 | 2026-09-14 | 2026-09-22 | 3
6.1.2 | Add cross-market contagion detection (one market shock propagating) | 7 | 2026-09-23 | 2026-10-01 | 3
6.1.3 | Implement model selection autopilot (best model per signal-target pair) | 7 | 2026-10-02 | 2026-10-10 | 3
6.1.4 | Add uncertainty quantification (prediction intervals, not just point estimates) | 10 | 2026-10-11 | 2026-10-23 | 3
6.2 | Track B: Build Errors → 5% | 30 | 2026-09-14 | 2026-10-23 | 2
6.2.1 | Implement self-healing builds (detect error → auto-apply fix → retry) | 10 | 2026-09-14 | 2026-09-27 | 3
6.2.2 | Add template versioning with A/B testing (new vs old templates) | 10 | 2026-09-28 | 2026-10-11 | 3
6.2.3 | Implement build quality gate (block deploy if quality < threshold) | 10 | 2026-10-12 | 2026-10-23 | 3
6.3 | Track C: Exploitation Accuracy → 75% | 30 | 2026-09-14 | 2026-10-23 | 2
6.3.1 | Add market timing model (when to launch, not just what to build) | 10 | 2026-09-14 | 2026-09-27 | 3
6.3.2 | Add user acquisition cost prediction from similar product data | 10 | 2026-09-28 | 2026-10-11 | 3
6.3.3 | Add churn prediction for deployed products | 10 | 2026-10-12 | 2026-10-23 | 3
6.4 | Track D: Build Automation → 2 hours | 30 | 2026-09-14 | 2026-10-23 | 2
6.4.1 | Full zero-touch pipeline: recommendation → build → deploy → monitor → scale | 10 | 2026-09-14 | 2026-09-27 | 3
6.4.2 | Add automated A/B testing for deployed apps | 10 | 2026-09-28 | 2026-10-11 | 3
6.4.3 | Add automated pricing optimization based on conversion data | 10 | 2026-10-12 | 2026-10-23 | 3
6.5 | Track E: Data Scale → 7TB | 30 | 2026-09-14 | 2026-10-23 | 2
6.5.1 | Add real-time streaming (Kafka/Redis Streams for sub-minute data) | 10 | 2026-09-14 | 2026-09-27 | 3
6.5.2 | Add sensor/IoT data ingestion (via MQTT broker) | 10 | 2026-09-28 | 2026-10-11 | 3
6.5.3 | Implement federated querying across PostgreSQL + S3 + streaming | 10 | 2026-10-12 | 2026-10-23 | 3
6.6 | Track F: Pricing Intelligence v2 | 30 | 2026-09-14 | 2026-10-23 | 2
6.6.1 | Implement dynamic pricing engine (A/B test prices per region) | 7 | 2026-09-14 | 2026-09-22 | 3
6.6.2 | Add currency conversion + PPP-adjusted pricing per country | 7 | 2026-09-23 | 2026-10-01 | 3
6.6.3 | Add price elasticity estimation from traffic → conversion data | 7 | 2026-10-02 | 2026-10-10 | 3
6.6.4 | Revenue-optimal pricing recommendations per app per region | 10 | 2026-10-11 | 2026-10-23 | 3
6.7 | M5 - Autonomous Operations Complete | 0 | 2026-10-23 | 2026-10-23 | 1
7 | M6 - Intelligence Engine | 30 | 2026-10-26 | 2026-12-04 | 1
7.1 | Track A: Model Accuracy → 85% | 30 | 2026-10-26 | 2026-12-04 | 2
7.1.1 | Add reinforcement learning for trading strategy optimization | 10 | 2026-10-26 | 2026-11-08 | 3
7.1.2 | Implement model distillation (compress ensemble into fast inference) | 10 | 2026-11-09 | 2026-11-22 | 3
7.1.3 | Add causal discovery (beyond Granger to structural causal models) | 10 | 2026-11-23 | 2026-12-04 | 3
7.2 | Track B: Self-Optimizing Builds | 30 | 2026-10-26 | 2026-12-04 | 2
7.2.1 | AI generates feature requirements from opportunity analysis (no YAML needed) | 10 | 2026-10-26 | 2026-11-08 | 3
7.2.2 | Auto-select best scaffold and tech stack per opportunity | 10 | 2026-11-09 | 2026-11-22 | 3
7.2.3 | Builds generate their own tests and validation suites | 10 | 2026-11-23 | 2026-12-04 | 3
7.3 | Track C: Exploitation Accuracy → 80% | 30 | 2026-10-26 | 2026-12-04 | 2
7.3.1 | Portfolio optimization across all deployed apps | 10 | 2026-10-26 | 2026-11-08 | 3
7.3.2 | Resource re-allocation recommendations (scale winners, sunset losers) | 10 | 2026-11-09 | 2026-11-22 | 3
7.3.3 | Auto-sunset underperforming products | 10 | 2026-11-23 | 2026-12-04 | 3
7.4 | Track D: Data Scale → 10TB | 30 | 2026-10-26 | 2026-12-04 | 2
7.4.1 | Full multi-source streaming ingestion operational | 10 | 2026-10-26 | 2026-11-08 | 3
7.4.2 | Automated data quality monitoring and anomaly detection | 10 | 2026-11-09 | 2026-11-22 | 3
7.4.3 | Data lineage tracking (know provenance of every prediction) | 10 | 2026-11-23 | 2026-12-04 | 3
7.5 | Track E: Revenue Engine | 30 | 2026-10-26 | 2026-12-04 | 2
7.5.1 | Central dashboard: portfolio MRR, CAC, LTV, churn by app | 7 | 2026-10-26 | 2026-11-03 | 3
7.5.2 | Automated financial reporting (monthly P&L per product) | 7 | 2026-11-04 | 2026-11-12 | 3
7.5.3 | Revenue alerts and anomaly detection | 7 | 2026-11-13 | 2026-11-21 | 3
7.5.4 | Investment-ready metrics dashboard | 10 | 2026-11-22 | 2026-12-04 | 3
7.6 | M6 - Intelligence Engine Complete | 0 | 2026-12-04 | 2026-12-04 | 1
8 | M7 - Market Leadership | 45 | 2026-12-07 | 2027-02-05 | 1
8.1 | Track A: Model Accuracy → 90% | 45 | 2026-12-07 | 2027-02-05 | 2
8.1.1 | Continuous learning pipeline (models retrain and auto-promote) | 15 | 2026-12-07 | 2026-12-27 | 3
8.1.2 | Model marketplace (share/sell prediction models to other users) | 15 | 2026-12-28 | 2027-01-17 | 3
8.1.3 | Multi-asset class prediction (stocks, crypto, commodities, real estate) | 15 | 2027-01-18 | 2027-02-05 | 3
8.2 | Track B: Full Automation | 45 | 2026-12-07 | 2027-02-05 | 2
8.2.1 | End-to-end: signal detected → app built → deployed → monetized → optimized | 15 | 2026-12-07 | 2026-12-27 | 3
8.2.2 | Average deployment time consistently under 2 hours | 15 | 2026-12-28 | 2027-01-17 | 3
8.2.3 | Build error rate sustained below 5% | 15 | 2027-01-18 | 2027-02-05 | 3
8.3 | Track C: Exploitation Accuracy → 90% | 45 | 2026-12-07 | 2027-02-05 | 2
8.3.1 | Multi-factor scoring validated against 12+ months of outcomes | 15 | 2026-12-07 | 2026-12-27 | 3
8.3.2 | Automated opportunity discovery (system finds BUILD opportunities) | 15 | 2026-12-28 | 2027-01-17 | 3
8.3.3 | Cross-opportunity synergy detection (complementary products) | 15 | 2027-01-18 | 2027-02-05 | 3
8.4 | Track D: Revenue Targets | 45 | 2026-12-07 | 2027-02-05 | 2
8.4.1 | 4-10 deployed apps generating subscription revenue | 11 | 2026-12-07 | 2026-12-21 | 3
8.4.2 | Region-specific pricing active in 10+ markets | 11 | 2026-12-22 | 2027-01-05 | 3
8.4.3 | Central revenue dashboard with real-time MRR tracking | 11 | 2027-01-06 | 2027-01-20 | 3
8.4.4 | Target: $20K+ MRR across portfolio | 12 | 2027-01-21 | 2027-02-05 | 3
8.5 | M7 - Market Leadership Complete | 0 | 2027-02-05 | 2027-02-05 | 1

## Milestone Roadmap
Milestone | Weeks | Model Accuracy | Exploitation Accuracy | Build Errors | Deploy Time | Data Scale | Revenue/Pricing
M0: Instrument & Measure | 1-3 | Baseline (~50%) | Baseline (~45-50%) | Baseline (~20-30%) | Current (5+ hrs) | ~50MB | Audit Stripe baseline
M1: Foundation Scaling | 4-9 | 60% | 55% | 25% | Measured | 100GB | Revenue Dashboard v1
M2: Intelligence Layer | 10-15 | 65% | 60% | 20% | 4 hours | 500GB | Cross-app revenue tracking
M3: Self-Learning Foundation | 16-21 | 70% | 65% | 15% | 3 hours | 1TB | Pricing Intelligence v1
M4: Scale & Optimize | 22-27 | 75% | 70% | 10% | 2.5 hours | 3TB | Revenue Dashboard v2 + P&L
M5: Autonomous Operations | 28-33 | 80% | 75% | 5% | 2 hours | 7TB | Dynamic Pricing Engine
M6: Intelligence Engine | 34-39 | 85% | 80% | Self-optimizing | Self-optimizing | 10TB | Portfolio Optimization
M7: Market Leadership | 40-48 | 90% | 90% | <5% sustained | < 2 hrs sustained | 10TB+ | Full Financial OS ($20K+ MRR)

## M0 - Instrument & Measure
M0 - Instrument & Measure ¦ Weeks 1-3
You can't improve what you can't measure
Track | Focus Area | Actions | Method / Rationale
Track A | Model Accuracy Baseline | • Run prediction validation on all matured predictions: POST /predictions/validate • Record baseline direction_accuracy, avg_error_pct, avg_change_error_pct • Add automated weekly validation cron (APScheduler or Railway cron) • Add accuracy trend chart to Prediction Accuracy tab | Documented baseline accuracy (~50-55%)
Track B | Build Error Baseline | • Add BuildMetrics tracking to build_feature.py (syntax/test/frontend/wiring errors) • Store results in JSON artifact uploaded with GitHub Actions • Parse artifact in a /builds/metrics endpoint | Error rate measurement framework, initial baseline (~20-30%)
Track C | Exploitation Metrics Baseline | • Tag all 103 BUILD recommendations with viability scores • Manually validate 10-20 BUILD recommendations against real-world outcomes • Create exploitation_validation table for outcome tracking | Documented baseline viability accuracy (~45-50%)
Track D | Revenue Baseline | • Audit Stripe dashboard for current subscriber count and MRR • Document current revenue per app | Revenue baseline document
Verification Criteria
✓ All 4 baselines documented with numbers
✓ Automated weekly validation running
✓ Build error tracking live in CI/CD

## M1 - Foundation Scaling
M1 - Foundation Scaling ¦ Weeks 4-9
Target: +5% accuracy (55→60%), data to ~100GB
Track | Focus Area | Actions | Method / Rationale
Track A | Model Accuracy → 60% | • Add daily Wikipedia pageview ingestion (55 vars × 365 days = 20K new records/year) • Add daily Reddit activity ingestion for top 30 subreddits • Implement walk-forward validation (train on N months, predict N+1, slide) • Add multi-lag Granger testing (1-12 month lags) | More granular data + proper validation → reduces overfitting
Track B | Build Errors → 25% | • Add pre-build template validation (lint templates before generation) • Add automated import resolution (detect missing imports, auto-add) • Add structured error reporting to GitHub Actions artifacts | Catch common failures before they happen
Track C | Exploitation Accuracy → 55% | • Backtest viability scores against 6-month historical data • Calibrate viability scoring weights based on backtest results • Add target_growth_actual field for outcome tracking | Empirical calibration of scoring model
Track D | Data Infrastructure | • Enable TimescaleDB extension on Railway PostgreSQL • Convert time_series_data to hypertable with time-based partitioning • Add automated data retention policy (raw: 2 years, aggregated: forever) • Set up S3 bucket for cold storage archive • Connection pool tuning: pool_size=20, max_overflow=10 | ~100GB target
Track E | Revenue Dashboard v1 | • Create RevenueEvent model (app_id, event_type, amount, currency, region, timestamp) • Create /revenue/dashboard endpoint aggregating across all Stripe accounts • Wire Stripe webhook events for all deployed apps to central tracker • Build basic Revenue tab (MRR chart, subscriber count, per-app breakdown) | Central webhook receiver that all deployed apps POST to
Verification Criteria
✓ Walk-forward validation shows 60%+ direction accuracy
✓ Build error rate measured with baseline established
✓ TimescaleDB partitioning active, daily ingestion running
✓ Revenue dashboard shows real MRR data

## M2 - Intelligence Layer
M2 - Intelligence Layer ¦ Weeks 10-15
Target: 65% accuracy, 60% exploitation, build time → 4hrs, errors → 20%
Track | Focus Area | Actions | Method / Rationale
Track A | Model Accuracy → 65% | • Add ensemble model: Granger causality + linear regression + ARIMA • Implement confidence-weighted ensemble (weight by historical accuracy) • Add feature engineering: rolling averages (7d/30d/90d), rate of change, volatility • Add cross-validation signal confidence (Wikipedia + Reddit agreement score) | Ensemble reduces individual model bias
Track B | Build Errors → 20% | • Add AI-powered code review step (LLM validates before commit) • Add integration test templates for common patterns (CRUD, auth, Stripe) • Fix top 5 most common build failure patterns from M1 data | Systematic failure pattern elimination
Track C | Exploitation Accuracy → 60% | • Add Google Trends integration (pytrends with proxy rotation) • Cross-reference viability scores with Google Trends search volume • Add competition scoring from real arXiv citation counts | Richer data inputs → more accurate viability
Track D | Build Automation → 4 hours | • Automate GitHub repo creation via GitHub API • Auto-generate Railway project via Railway API • Auto-wire Stripe subscription (create product + price via API) • Auto-inject GA4 measurement ID from analytics template | One-click Build & Deploy from Exploitation Board
Track E | Data Scale → 500GB | • Add FRED economic indicators (50+ variables: GDP, CPI, unemployment) • Add Alpha Vantage intraday data for top 10 stocks (5-min intervals) • Add news sentiment from GDELT API (daily event counts by theme) • Set up ETL pipeline with batch scheduling (APScheduler) | More diverse, higher-frequency data sources
Verification Criteria
✓ Ensemble model shows 65%+ direction accuracy on walk-forward test
✓ Build → deploy → live app achievable in 4 hours with automation
✓ Revenue dashboard tracking deployed app(s)

## M3 - Self-Learning Foundation
M3 - Self-Learning Foundation ¦ Weeks 16-21
Target: 70% accuracy, 65% exploitation, build time → 3hrs, errors → 15%
Track | Focus Area | Actions | Method / Rationale
Track A | Model Accuracy → 70% | • Implement automatic model retraining when accuracy drops below threshold • Add prediction feedback loop: validated predictions → retrain features • Add anomaly detection (Z-score) to flag unusual signals • Implement adaptive lag selection (dynamically adjust based on recent accuracy) | System learns from its own prediction outcomes
Track B | Build Errors → 15% | • Build error pattern classifier (import, syntax, config, runtime categories) • Auto-fix common patterns (missing __init__.py, wrong imports, missing env vars) • Add scaffold regression tests (test each template produces working code) | Error taxonomy → targeted fixes → prevent recurrence
Track C | Exploitation Accuracy → 65% | • Track actual outcomes of PURSUING recommendations • Add time-to-market analysis (recommendation → live product duration) • Calibrate opportunity_duration_months against actual windows | Closed-loop validation against real deployment outcomes
Track D | Build Automation → 3 hours | • Add automated domain configuration (subdomain allocation) • Add automated SSL certificate provisioning • Add automated database setup for deployed apps • Add post-deploy health check + smoke test | Remove remaining manual steps
Track E | Data Scale → 1TB | • Add social media feeds (Twitter/X academic API for trend data) • Add IoT starter: OpenWeather API for 100 cities (hourly) • Add Pushshift/Pullpush for full Reddit historical data • Implement data compression in TimescaleDB (compress chunks >7 days old) | Breadth of sources + compression for storage efficiency
Track F | Pricing Intelligence v1 | • Add IP geolocation to dashboard (MaxMind GeoLite2 free database) • Map regions to PPP tiers from World Bank API • Create pricing_recommendation table (region, suggested_price, confidence) • Add traffic-based demand estimation per region | Traffic patterns + economic data → region-aware pricing
Verification Criteria
✓ Self-retraining loop running automatically on weekly schedule
✓ Accuracy at 70%+ with feedback loop active
✓ Pricing intelligence generating region-specific suggestions
✓ 1TB data threshold reached

## M4 - Scale & Optimize
M4 - Scale & Optimize ¦ Weeks 22-27
Target: 75% accuracy, 70% exploitation, build time → 2.5hrs, errors → 10%
Track | Focus Area | Actions | Method / Rationale
Track A | Model Accuracy → 75% | • Add LSTM/transformer-based time series model (PyTorch) as ensemble member • Implement feature importance ranking (SHAP values) for interpretability • Add regime detection (bull/bear/sideways affect model choice) • Implement online learning (update model incrementally with new data) | Deep learning for non-linear patterns + regime-awareness
Track B | Build Errors → 10% | • Implement AI-powered scaffold improvement (analyze fails → update templates) • Add end-to-end integration test suite for full build pipeline • Add canary deployment (deploy to staging first, promote if healthy) | Self-improving templates based on failure analysis
Track C | Exploitation Accuracy → 70% | • Add competitive landscape analysis (how many similar apps exist?) • Cross-reference with Product Hunt / Indie Hackers for market validation • Add user engagement prediction model (predict DAU/MAU) | Market intelligence beyond statistical signals
Track D | Build Automation → 2.5 hours | • Add automated testing pipeline for deployed apps • Add automated monitoring setup (uptime, error rate, performance) • Add automated changelog and release notes generation | Reduce post-deployment manual work
Track E | Data Scale → 3TB | • Add Bloomberg/Reuters alternative data feeds (if budget allows) • Add satellite imagery analysis for economic indicators (nighttime lights) • Implement data lakehouse pattern (S3 + DuckDB + PostgreSQL hot data) | Alternative data + hybrid storage architecture
Track F | Revenue Dashboard v2 | • Add Google AdSense integration for ad-supported apps • Add per-app P&L tracking (revenue - infrastructure cost) • Add subscriber cohort analysis (retention by signup month) • Add revenue forecasting from growth trends | Full financial visibility across portfolio
Verification Criteria
✓ Deep learning ensemble at 75%+ accuracy
✓ Build → deploy consistently under 2.5 hours
✓ Revenue dashboard showing all revenue streams (subscriptions + ads)
✓ 3TB data with hybrid hot/cold storage

## M5 - Autonomous Operations
M5 - Autonomous Operations ¦ Weeks 28-33
Target: 80% accuracy, 75% exploitation, build time → 2hrs, errors → 5%
Track | Focus Area | Actions | Method / Rationale
Track A | Model Accuracy → 80% | • Implement multi-horizon forecasting (1 week, 1 month, 3 month predictions) • Add cross-market contagion detection (one market shock propagating) • Implement model selection autopilot (best model per signal-target pair) • Add uncertainty quantification (prediction intervals, not just point estimates) | Multi-horizon + automatic model selection + uncertainty
Track B | Build Errors → 5% | • Implement self-healing builds (detect error → auto-apply fix → retry) • Add template versioning with A/B testing (new vs old templates) • Implement build quality gate (block deploy if quality < threshold) | Self-healing + quality gates
Track C | Exploitation Accuracy → 75% | • Add market timing model (when to launch, not just what to build) • Add user acquisition cost prediction from similar product data • Add churn prediction for deployed products | Full lifecycle prediction (build + launch + grow + retain)
Track D | Build Automation → 2 hours | • Full zero-touch pipeline: recommendation → build → deploy → monitor → scale • Add automated A/B testing for deployed apps • Add automated pricing optimization based on conversion data | Complete automation of all manual steps
Track E | Data Scale → 7TB | • Add real-time streaming (Kafka/Redis Streams for sub-minute data) • Add sensor/IoT data ingestion (via MQTT broker) • Implement federated querying across PostgreSQL + S3 + streaming | Real-time data foundation for time-critical signals
Track F | Pricing Intelligence v2 | • Implement dynamic pricing engine (A/B test prices per region) • Add currency conversion + PPP-adjusted pricing per country • Add price elasticity estimation from traffic → conversion data • Revenue-optimal pricing recommendations per app per region | Data-driven pricing optimization
Verification Criteria
✓ 80%+ accuracy with uncertainty intervals
✓ Zero-touch build-to-deploy in 2 hours
✓ Self-healing builds at <5% error rate
✓ Revenue dashboard with dynamic pricing active

## M6 - Intelligence Engine
M6 - Intelligence Engine ¦ Weeks 34-39
Target: 85% accuracy, 80% exploitation, self-optimizing
Track | Focus Area | Actions | Method / Rationale
Track A | Model Accuracy → 85% | • Add reinforcement learning for trading strategy optimization • Implement model distillation (compress ensemble into fast inference) • Add causal discovery (beyond Granger to structural causal models) | Advanced ML + causal inference
Track B | Self-Optimizing Builds | • AI generates feature requirements from opportunity analysis (no YAML needed) • Auto-select best scaffold and tech stack per opportunity • Builds generate their own tests and validation suites | AI writes its own specifications
Track C | Exploitation Accuracy → 80% | • Portfolio optimization across all deployed apps • Resource re-allocation recommendations (scale winners, sunset losers) • Auto-sunset underperforming products | Portfolio management approach
Track D | Data Scale → 10TB | • Full multi-source streaming ingestion operational • Automated data quality monitoring and anomaly detection • Data lineage tracking (know provenance of every prediction) | Enterprise-grade data platform
Track E | Revenue Engine | • Central dashboard: portfolio MRR, CAC, LTV, churn by app • Automated financial reporting (monthly P&L per product) • Revenue alerts and anomaly detection • Investment-ready metrics dashboard | Full financial operating system
Verification Criteria
✓ 85%+ accuracy on 3-month forward predictions
✓ Self-generating build specifications
✓ Portfolio-level revenue optimization active
✓ 10TB data platform operational

## M7 - Market Leadership
M7 - Market Leadership ¦ Weeks 40-48
Target: 90% accuracy, 90% exploitation, market-ready
Track | Focus Area | Actions | Method / Rationale
Track A | Model Accuracy → 90% | • Continuous learning pipeline (models retrain and auto-promote) • Model marketplace (share/sell prediction models to other users) • Multi-asset class prediction (stocks, crypto, commodities, real estate) | Continuous improvement + market breadth
Track B | Full Automation | • End-to-end: signal detected → app built → deployed → monetized → optimized • Average deployment time consistently under 2 hours • Build error rate sustained below 5% | Mature, battle-tested automation
Track C | Exploitation Accuracy → 90% | • Multi-factor scoring validated against 12+ months of outcomes • Automated opportunity discovery (system finds BUILD opportunities) • Cross-opportunity synergy detection (complementary products) | Validated scoring + autonomous discovery
Track D | Revenue Targets | • 4-10 deployed apps generating subscription revenue • Region-specific pricing active in 10+ markets • Central revenue dashboard with real-time MRR tracking • Target: $20K+ MRR across portfolio | Portfolio scale + pricing optimization
Verification Criteria
✓ 90% direction accuracy on walk-forward (6-month window)
✓ 90% exploitation recommendation viability (validated)
✓ <5% build errors sustained over 3-month period
✓ 2-hour average deployment time sustained
✓ Revenue dashboard live with all apps reporting
✓ Dynamic pricing active in multiple regions

## Architecture Evolution
Milestone | Storage | Model Pipeline | Build Pipeline | Revenue System
M0 | PostgreSQL (14K records, ~50MB) | Granger causality only (granger_v1) | Manual build_feature.py + manual GitHub/Stripe (~5+ hrs) | Manual Stripe dashboard checks
M1 | + TimescaleDB extension + daily ingestion → 100GB | + Walk-forward validation + multi-lag testing | + Error tracking + pre-build validation | + Central RevenueEvent model + webhook aggregation
M2 | + Connection pool tuning + query optimization → 500GB | + Ensemble (Granger + linear + ARIMA) + feature engineering | + Auto GitHub repo + auto Railway + auto Stripe + auto GA4 (~4 hrs) | + Per-app MRR chart + subscriber counts
M3 | + Data compression + S3 cold storage → 1TB | + Feedback loop + auto-retrain + anomaly detection | + Auto domain + auto SSL + auto DB + smoke tests (~3 hrs) | + Geo-pricing intelligence v1
M4 | + DuckDB analytics layer + data lakehouse → 3TB | + LSTM/transformer + regime detection + online learning | + Staging/canary + auto monitoring (~2.5 hrs) | + Google Ads integration + per-app P&L + cohort analysis
M5 | + Kafka streaming + federated queries → 7TB | + Multi-horizon + uncertainty quantification + autopilot | + Self-healing + quality gates (~2 hrs) | + Dynamic pricing engine + A/B pricing
M6 | Full hybrid: TimescaleDB + S3 + Kafka → 10TB | + Causal discovery + reinforcement learning | + AI-generated specs + auto stack selection | + Portfolio optimization + auto-sunset
M7 | 10TB+ operational | + Continuous learning + multi-asset + model marketplace | + Zero-touch end-to-end pipeline | + Full financial OS + investment-ready dashboard

## Key Files
File | Purpose
revenue_models.py | RevenueEvent, SubscriptionMetric, PricingRecommendation models
revenue_router.py | Revenue dashboard endpoints
revenue_webhook.py | Central Stripe webhook receiver for all apps
pricing_engine.py | Region-aware pricing intelligence
model_ensemble.py | Ensemble prediction service
auto_retrain.py | Self-learning feedback loop
streaming_ingestion.py | Kafka/Redis Streams ingestion
build_error_tracker.py | Systematic build error classification
self_healing_builder.py | Auto-fix build failures